## Product Backlog
Tag | As a.... | I want to... | so that... | Sprint | Acceptance Criteria | Story Points | Status
US01 | Wellness User | be able to track daily calories | I can monitor my weight and food intake | 1 | - There is backend support for a user's daily calorie log - User can input foods they have eaten - User can select recommended meals and have it automatically be added to the calorie tracker - Calories eaten can be viewed as numbers or as a graph | 11 | Completed
US02 | Diet Tracker | be able to track calories over time | I can monitor food intake over time | 1 | - There is a screen for weekly and monthly calorie intake - User can view a graph of their food intake over a week or month | 5 | Completed
US03 | Nutrition Client | tell NutriAI what I am craving | that my meal plan can adapt while also support my goals | 2 | - There is a button on the dashboard that says I'm Craving... - When clicked the user will be prompted with "Sweet", "Savory", "Salty", etc. - When they choose what they are craving, the system will suggest a recipe/snack while also adapting to the users goals | 8 | Completed
US04 | Nutrition Client | tell NutriAI I am hungry | so that NutriAI can quickly suggest a meal that meets my goals | 2 | - There is a button on the dashboard that says I'm Hungry... - When clicked the user will be given a recipe based on their dietary restrictions and goals. | 8 | Completed
US05 | Diet Tracker | be able to search for foods and/or recipes in a database | I can log meals quickly | 2 | - User can search recipes based on food - Calories are automatically added to tracker - Ability or option to adjust serving size | 8 | Completed
US06 | Wellness User | be able to enter my health goal | NutriAI can calculate my recommended daily calorie intake | 1 | - User inputs height, weight, sex, birth date, and activity level - App calculates daily calorie target - User can edit health goal and activity level at any time | 5 | Completed
US07 | New User | create an account so that I can save my nutrition data | NutriAI can recommend my meals based on my profile | 1 | - User creates an account and enters their name, email, password - App prompts them with health/diet questions to build their profile | 5 | Completed
US08 | New User | enter dietary restrictions and allergies as that recommendations are safe. | To avoid any allergic reactions | 1 | - During account creation/profile setup, the app will ask them their dietary restrictions and allergies | 3 | Completed
US09 | Goal-Oriented User | track my weight and progress over time | I can see whether NutriAi is helping me reach my goals | 1 | - User will be required to enter their weight daily through the daily logs page - System will keep track of each log and show user a chart to see their progress | 3 | Completed
US10 | User | update my health profile | my food recommendations can be as accurate as possible | 2 | - User can edit their height, occupation, goals, etc. - Updated data recalculates calorie targets | 3 | Completed
US11 | Nutrition Client | NutriAI to learn which recommendations I actually use | future suggestions improve | 2 | - System records which recommendations are accepted and ignored - AI adjusts future recommendations based on acceptance rate - Frequently accepted meals will be prioritized | 13 | Completed
US12 | Nutrition Client | NutriAI to recommend healthier foods when I have a craving at night | I can avoid overeating before bed | 3 | - System detects the time a request was made - If the time is late at night, NutriAI suggests a lighter meal - Suggestions will prioritize low calorie snacks instead of meals | 5 | Completed
US13 | Nutrition Client | NutriAI to suggest alternatives if I don't like the recommendation | I can quickly find something I like | 2 | - After NutriAI suggests an item, users can click suggest another - System generates a new recommendation - New recommendations will be different from previous suggestions - User can repeat this as many times as they like | 3 | Completed
US14 | Diet Tracker | see when I usually eat my meals | I can understand my eating schedule | 2 | - System will log meal times - Charts will be shown to see trends over multiple days or weeks | 5 | Completed
US15 | Administrator | maintain a database of users | I can monitor site activity and understand user population | 1 | - User schema designed in database - User schema implemented in database - Users are able to sign into our app | 8 | Completed
US16 | Goal-Oriented User | NutriAI to motivate me when I'm fighting cravings. | I stay committed to my health goals. | 2 | - When a user selects craving a motivational message is displayed. - When a user selects craving the app offers suggesstions the redirects the user want - When a user selects craving it checks to see if they are actually craving and not hunger and redirect the user to click the I'm hungry button instead. - When a user selects craving it reminds the user of their end goal, and display their progress or short commings - When a user selects craving they can tell the app what they are craving and the app offers a better healthier solution. - When a user selects the craving button they can see a log of their cravings, frequency, and types of foods. - When a user selects craving they are asked if they successfully fought the craving or not and the system we keep a record of the user successfully fighting of cravings. - When the user select craving they are provide with a list of distractions to help fight the craving. | 15 | Completed
US17 | User | save my profile data | my nutrition recommendations can be personalized | 2 | User can enter profile data Data is saved successfully Data loads correctly on refresh Frontend and backend fields match | 8 | Completed
US18 | User | access a feature selection page | I can choose what I need quickly | 2 | - Features page exists - Page displays two options - I'm Hungry and I'm Craving - Buttons are visible and clickable | 3 | Completed
US19 | Nutrition Client | tell NutriAI I am hungry | NutriAI can guide me to the right meal | 2 | - Clicking I'm Hungry routes to Hunger Check page - Hunger Check evaluates user inputs - User is routed to /hungry if conditions are met | 8 | Completed
US20 | Wellness User | have NutriAI check if I am actually hungry | I can avoid confusing cravings with real hunger | 2 | - Hunger Check page exists - User inputs hunger level, energy, and hunger signals - System calculates score - System determines hunger vs craving | 5 | Completed
US21 | Nutrition Client | see a basic meal suggestion page | I can view a recommended meal | 2 | - /hungry page exists - Displays a sample meal - Shows basic nutrition info - Includes actions like Eat this or Swap | 5 | Completed
US22 | Nutrition Client | tell NutriAI I am craving | NutriAI can guide me to better alternatives | 2 | - Clicking I'm Craving routes to Craving Check page - Craving Check evaluates user inputs - System determines if craving or actual hunger - If craving, user is routed to /craving - Craving page shows alternative suggestions | 8 | Completed
US23 | Wellness User | the system to calculate my BMI using my height and weight | I can understand if my weight is in a healthly range | 1 | - When a user enters height and weight and clicks calculate BMI, the system sends a request to the api for the BMI value - The system returns a calculated BMI value - The BMI value is displayed on the profile summary panel. - The BMI category is shown (Underweight, Normal Weight, Overweight, Obese) - If height or weight is missing, the system shows an error message. | 3 | Completed
US24 | Wellness User | the system to calculate my energy score | I can understand my current energy level based on my habits. | 1 | - When the user clicks Calculate BMI and Energy, the system sends a request to the API - The API returns an energy score between 0-100 - The energy score updates the Energy Meter Progress bar - If the API fails, an error message is displayed. | 5 | Completed
US25 | User | a profile page where I can enter and update my personal health information. | the app can store my information, calculate my BMI, energy level, and personalize recommendations. | 1 | - When a user navigates to the profile page, they can enter personal health information such as height and weight. | 5 | Completed
US26 | User | the system to save my profile and load my data automatically. | I don't have to re-enter my health information every time. | 1 | - When the profile page loads, the system calls api/profile - If a profile exists, the form fields are populated with saved values | 3 | Completed
US27 | Nutrition Client | have NutriAI analyze my diet. | I understand what nutrients I may be missing | 3 | - NutriAI analyzes foods logged in daily logs - The system compares intake with recommended nutrition values - NutriAI displays nutrient deficiencies to the user | 8 | Completed
US28 | Goal-Oriented User | see my saved goal in my profile | I can stay motivated to reach my target. | 2 | - Goals page saves the selected goal to the user profile - Profile page displays the saved goal - User can update their goal - Saved goal data loads correctly when the page refreshes | 3 | Completed
US29 | Nutrition Client | get meal ideas using ingredients I already have. | I can cook realistic meals without buying extra food. | 3 | - User can enter ingredients they have for more customized meals suggesstions vs random ones. - NutriAI suggests meals using those ingredients. - Meals align with calorie goals and restrictions | 8 | Completed
US30 | Diet Tracker | view a weekly nutrition summary. | I understand how well I followed my plan. | 3 | - NutriAi generates weekly report - Report shows calories and nutirent balance. - Report highlights patterns or trends. | 5 | Completed
US31 | User | receive reminders to log meals. | I keep my food tracking accurate. | 3 | - The App detects when meals aren't logged. - The system sends reminder notifications to log meals - User can enable or disable reminders | 5 | Completed
US32 | Goal-Oriented User | have NutriAI manage a guide my weight goals. | I can reach and maintain my target weight. | 3 | - User can set a target weight in their profile - System tracks weight enties over time - System alerts the user if weight changes too quickly or too slowly | 3 | Completed
US33 | Wellness User | have NutriAI check if I am actually craving | I can understand why I want certain foods and make better choices | 2 | - Craving Check page exists - User selects craving intensity using a scale with clear labels - User answers questions about specific food, recent eating, fullness, physical hunger signals, emotional triggers, hydration, sleep, and stress - System calculates a score based on inputs - System displays a result summary with score - Continue button routes user to /craving if craving or /hungry if not | 5 | Completed
US34 | Goal-Oriented User | set and view my goal based on my profile | I understand my current status and how far I am from my target so NutriAI can guide my decisions | 2 | - Goal page exists - User selects a goal (lose, maintain, gain, energy) - Profile data (height and weight) is loaded and displayed - BMI is calculated and shown - User enters target weight - System shows how many pounds to gain or lose - Goal summary displays selected goal and focus | 8 | Completed
US35 | User | select diet restrictions | my meal recommendations match my dietary needs | 2 | - User can select multiple diet restrictions from checklist - Selections are saved to profile - Selections load correctly on refresh | 5 | Completed
US36 | User | select medical history | my recommendations account for health conditions | 2 | - User can select multiple medical conditions from checklist - Selections are saved to profile - Selections load correctly on refresh | 5 | Completed
|  | TOTAL: |  |  |  | 157 | Completed